## Sheet1
Milestones | Expected Date of Completion | Actual Date of Completion | Reasons for Non Completion
Requirements gathering | 2020-09-21 | 2020-09-20
Design& Analysis | 2020-09-28 | 2020-09-28
Backend Development | 2020-11-10 |  | Requiremnts Creep, Tools chosen to handle payment couldn't handle requirements so I started a new technology using Django, deadline was closer than I thought(
Frontend Development | 2020-11-23 | 2020-11-23
Unit Testing | 2020-11-26 | 2020-11-23
Regression Testing | 2020-11-25 | 2020-11-23
System Testing | 2020-12-08 |  | Backend wasn’t finished so I couldn’t test out the entire system that I had in mind
Project Presentation | 2020-12-08 |  | To be presented on 11/30/2020